## Sheet1
Weekly Project Plan Update (Gantt Chart)
Sashimi © 2024 Tom Keir (SDD Assessment 3)
Task | Notes | Start Date | Expected Completion | Actual Completion | Term 1 | [5 empty] | Holiday |  | Term 2
[5 empty] | 6 | 7 | 8 | 9 | 10 | 11 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Software
Design Screens | UI without functionality | T1W6 | T1W9 | T1W7 | bar: Term 1 6 to Term 1 9
Design Folder and Database Structure | Athlete data spreadsheet, folder hierarchy, etc | T1W8 | T1W9 | T1W7 | bar: Term 1 8 to Term 1 9
Develop Carnival Functionality | Import, Save, Manage Carnivals | T1W10 | Holiday W2 | T2W4 | bar: Term 1 10 to Holiday 2
Develop Athlete/Event Functionality | Athlete list, event list, creation/edit funcitons. | Holiday W2 | T2W3 | T2W4 | bar: Holiday 2 to Term 2 3
Develop Scoring Functionality | Score and Print event ranks | T2W2 | T2W4 | T2W3 | bar: Term 2 2 to Term 2 4
Testing
Develop Test Functions | Test Algorithms | T2W5 | T2W6 | T2W6 | bar: Term 2 5 to Term 2 6
Debug | Fix | T2W5 | T2W6 | T2W8 | bar: Term 2 5 to Term 2 6
Client Feedback
Client Meeting | Sit down with client, discuss functionality | T2W5 | T2W6 | T2W8 | bar: Term 2 5 to Term 2 6
Make Necessary Adjustments | Final changes | T2W5 | T2W7 | T2W8 | bar: Term 2 5 to Term 2 7
Final
Publish | Build application, icon, etc. | T2W7 | T2W8 | T2W8 | bar: Term 2 7 to Term 2 8